## Sheet1
Rpath punchlist
Item | Action Type | Description | Lead | Status | Deadline
Convert to data.table | coding | The R package data.table handles large data well without copying entire data frames when adding columns | Sean | Done | 2014-12-22
S3 object | coding | Develop class definitions for ecopath object outputed from ecopath() | Sean | Done – created Rpath object in ecopath() | 2014-12-22
summary(ecopath.obj) | coding | Develop output for summary function using ecopath object | Sean | First pass done | 2015-01-01
plot(ecopath.obj) | coding | Develop food web plot for plot function using ecopath object | Sean |  | 2015-01-01
Convert to RCPP | coding | The R package RCPP integrates R and C++ directly, may gain efficiency in ecosim() | Sean
Rpath package | coding | Assemble ecopath() and ecosim() into an Rpath package | Sean |  | 2015-01-15
Georges Bank | model dev | Balance new Georges Bank model | Sean | Started...need to add multiple stanzas and redo diet matrix | 2015-01-09
Develop metrics to compare EwE with Rpath | model dev | Residuals between EwE and Fortran model have been used | Sarah
Rpath manuscript | manuscript | Special issue of Ecological Modelling based on Ecopath Conference | Sean | Outline circulated...first draft should be finalized by mid-January | 2015-02-28
Rpath Beta Test | model dev | Send Rpath package to a limited number of users to kick the tires | Sean | List of potential testers has been compiled | 2015-02-01
Shiny outputs | coding | The R package shiny allows for html type outputs that are interactive | Sean | There are Atlantis versions of some of these tools...probably won't be ready for initial release
Time series fitting | coding | Allow users to fit to time series | ? | C code already exists? - Kerim may hire a programmer to do this next fall